## Closeout Checklist
[5 empty] | GR Section | GCs Section
[5 empty] | 01 77 00 | 10.6, 10.7 10.8 10.9
01 78 23
01 78 39
01 91 00
ADMINISTRATIVE |  |  |  |  | 01 91 13
As Built Redlines
Permits Closed
Submittals Closed
Formal Closeout Submittal Packages
RFI's responded to and closed
Contractors Daily Logs
Incident Reports - Injuries or Property Damage
OCIP Closeout Process
ADA scope cost tabulation
Permits - cost tabulation
Return of any keys checked out
FINANCIAL
Change Order Proposals dispositioned and closed
Change Orders issued executed and processed
Substantial Completion Payment
Final payment with releases and declarations
Final statement of accounts
Sworn statement final payments to subcontractors and suppliers
Unconditional releases
Contract & Purchase Order closeouts
Written verification with vendors - all invoicing processed and paid
Close PO's
Work Order Closeout
CLOSEOUT PROCEDURES |  |  |  |  | 01 77 00
Substantial Completion
OAC Punch Lists
As Builts & Record Documents
O&M Data
Demonstration & Training
Final construction photos
|  | Statement of Cx Completion |  |  | 01 91 13
Complete startup and testing for systems and equipment
Perform preventative maintenance on equipment used prior to Substantial Completion
Inspect, test, and adjust performance of every system to ensure compliance
Check fluid and gas carrying pipe systems, roofs, flashing, gutters, and downspouts for leaks
Insurance changeover requirements
Permanent locks installed
Changeover of utilities
Terminate and remove temporary facilities from Project Site
Inspection and walkthrough with local emergency responders
Touch up and otherwise repair and restore marred exposed finishes
Complete final cleaning
Certificate of Substantial Completion
| Final Completion |  |  |  | 01 77 00
Certified List of Incomplete Items
Certificate of Insurance
Pest Control final inspection and warranty
Submit all permit and inspection records for project
PROJECT RECORD DOCUMENTS |  |  |  |  | 01 78 39
General
Electronic Files: All electronic files organized per Volume
All files are in PDF format or native format and follow the USC Nomenclature Standard for file naming
As Built Drawings & Specifications
Electronic copy - pdf format
Stamped "As Built"
Record Drawings by AE Team
Electronic copies in pdf and dwg formats
Stamped "Record Document"
Record Models by AE and GC Teams
Electronic copy in REVIT format
Referenced as "Record Document"
Record Survey Data
Electronic copies in pdf and dwg formats
Stamped "Record Document"
Contents
Utility as builts including survey data of utility locations
Certified final property survey
Record Specifications
Electronic copy - pdf format
Stamped "Record Document"
Record Submittals / Product Data
Electronic copy - pdf format
Record Test Certificates
Electronic copy - pdf format
Permit & Inspection Records
Electronic copy - pdf format
Storm Water Pollution Prention Program (SWPPP)
Electronic copy - pdf format
Approved LID Program
Record O&M Covenant
SWPPP observation forms stamped by EOR
Miscellaneous Record Submittals
Electronic copy - pdf format
OPERATIONS AND MAINTENANCE DATA |  |  |  |  | 01 78 23
O&M Manuals
Electronic copy - pdf format
Organized by SpecSection, Trade, Major Systems, Equipment, Finishes
Each digital binder submitted is labeled with the Project Name, Number, and appropriate Volume number.
Each digital binder includes a full Table of Contents
All files are in PDF format and follow the USC Nomenclature Standard for file naming
O&M Manual Contents
Facility Information
Contact Directory
Warranty Information
Equipment nameplate data
Materials & Finishes Information
Source Information
Product Information
Maintenance Procedures
As-built data (Material/Finish Schedule)
Systems & Equipment Information
Contractor Information
System Flow Diagrams
Operation & Maintenance Instructions
Panel Board Circuit Directories
Valve Charts
Attic Stock
Attic stock delivered with tansmittals and acknowledgements of receipt
Inventory spread sheet
All stock labeled with Manufacturer name and model number
SYSTEMS DEMONSTRATION AND TRAINING |  |  |  |  | 01 79 00
Training Manual
Electronic copy - pdf format - for each system or equipment demonstrated and trained
Contents
Agendas
Training Schedule
Sign-In Sheets
Training Handouts
Include contact information for training videographer
Training Recordings
Digital video format
Organized according to training schedule
Digital video file naming should include project name and PR #

## Demo
ADMINISTRATIVE - GR 01 91 13
# | Sub-Category | Applicable | Reference Link | Date of Completion | Date Approved | Person Responsible | Notes
A1 | As Built Redlines | FALSE
A2 | Permits Closed | FALSE
A3 | Submittals Closed | FALSE
A4 | Formal Closeout Submittal Packages | TRUE
A5 | RFI's responded to and closed | FALSE
A6 | Contractors Daily Logs | FALSE
A7 | Incident Reports - Injuries or Property Damage | FALSE
A8 | OCIP Closeout Process | FALSE
A9 | ADA scope cost tabulation | TRUE
A10 | Permits - cost tabulation | TRUE
A11 | Return of any keys checked out | TRUE
FINANCIAL
# | Sub-Category | Applicable | Reference Link | Date of Completion | Date Approved | Person Responsible | Note
F1 | Change Order Proposals dispositioned and closed | FALSE
F2 | Final payment with releases and declarations | FALSE
F3 | Sworn statement final payments to subcontractors and suppliers | TRUE
F4 | Change Orders issued executed and processed | TRUE
F5 | Substantial Completion Payment | TRUE
F6 | Final statement of accounts | FALSE
F7 | Unconditional releases | FALSE
F8 | Contract & Purchase Order closeouts | FALSE
F9 | Written verification with vendors - all invoicing processed and paid | TRUE
F10 | Close PO's | TRUE
F11 | Work Order Closeout | TRUE
CLOSEOUT PROCEDURES
# | Sub-Category | Applicable | Reference Link | Date of Completion | Date Approved | Person Responsible | Note
C1 | OAC Punch Lists | FALSE
C2 | As Builts & Record Documents | FALSE
C3 | O&M Data | FALSE
C4 | Demonstration & Training | FALSE
C5 | Final construction photos | TRUE
C6 | Statement of Cx Completion - GR 01 91 13
C7 | Complete startup and testing for systems and equipment | FALSE
C8 | Perform preventative maintenance on equipment used prior to Substantial Completion | FALSE
C9 | Inspect, test, and adjust performance of every system to ensure compliance | FALSE
C10 | Check fluid and gas carrying pipe systems, roofs, flashing, gutters, and downspouts for leaks | FALSE
C11 | Insurance changeover requirements | TRUE
C12 | Permanent locks installed | FALSE
C13 | Changeover of utilities | FALSE
C14 | Terminate and remove temporary facilities from Project Site | FALSE
C15 | Inspection and walkthrough with local emergency responders | FALSE
C16 | Touch up and otherwise repair and restore marred exposed finishes | FALSE
C17 | Complete final cleaning | FALSE
C18 | Certificate of Substantial Completion | FALSE
C19 | Certified List of Incomplete Items | FALSE
C20 | Certificate of Insurance | TRUE
C21 | Pest Control final inspection and warranty | FALSE
C22 | Submit all permit and inspection records for project | FALSE
PROJECT RECORD DOCUMENTS
# | Sub-Category | Applicable | Reference Link | Date of Completion | Date Approved | Person Responsible | Note
P1 | General
P2 | Electronic Files: All electronic files organized per Volume | TRUE
P3 | All files are in PDF format or native format and follow the USC Nomenclature Standard for file naming | TRUE
P4 | As Built Drawings & Specifications | TRUE
P5 | Electronic copy - pdf format | FALSE
P6 | Stamped "As Built" | TRUE
P7 | Record Drawings by AE Team | FALSE
P8 | Electronic copies in pdf and dwg formats | FALSE
P9 | Stamped "Record Document" | FALSE
P10 | Record Models by AE and GC Teams | FALSE
P11 | Electronic copy in REVIT format | FALSE
P12 | Referenced as "Record Document" | FALSE
P13 | Record Survey Data | FALSE
P14 | Electronic copies in pdf and dwg formats | FALSE
P15 | Stamped "Record Document" | FALSE
P16 | Contents | TRUE
P17 | Utility as builts including survey data of utility locations | TRUE
P18 | Certified final property survey | FALSE
P19 | Record Specifications | FALSE
P20 | Electronic copy - pdf format | FALSE
P21 | Stamped "Record Document" | FALSE
P22 | Record Submittals / Product Data | FALSE
P23 | Electronic copy - pdf format | TRUE
P24 | Record Test Certificates | TRUE
P25 | Electronic copy - pdf format | TRUE
P26 | Permit & Inspection Records | FALSE
P27 | Electronic copy - pdf format | FALSE
P28 | Storm Water Pollution Prention Program (SWPPP) | FALSE
P29 | Electronic copy - pdf format | FALSE
P30 | Approved LID Program | FALSE
P31 | Record O&M Covenant | TRUE
P32 | SWPPP observation forms stamped by EOR | FALSE
P33 | Miscellaneous Record Submittals | FALSE
P34 | Electronic copy - pdf format | FALSE
OPERATIONS AND MAINTENANCE DATA
# | Sub-Category | Applicable | Reference Link | Date of Completion | Date Approved | Person Responsible | Note
O1 | O&M Manuals
O2 | Electronic copy - pdf format | FALSE
O3 | Organized by SpecSection, Trade, Major Systems, Equipment, Finishes | FALSE
O4 | Each digital binder submitted is labeled with the Project Name, Number, and appropriate Volume number. | FALSE
O5 | Each digital binder includes a full Table of Contents | FALSE
O6 | All files are in PDF format and follow the USC Nomenclature Standard for file naming | FALSE
O7 | O&M Manual Contents | FALSE
O8 | Facility Information | FALSE
O9 | Contact Directory | FALSE
O10 | Warranty Information | FALSE
O11 | Equipment nameplate data | FALSE
O12 | Materials & Finishes Information | FALSE
O13 | Source Information | FALSE
O14 | Product Information | TRUE
O15 | Maintenance Procedures | TRUE
O16 | As-built data (Material/Finish Schedule) | FALSE
O17 | Systems & Equipment Information | TRUE
O18 | Contractor Information | FALSE
O19 | System Flow Diagrams | FALSE
O20 | Operation & Maintenance Instructions | FALSE
O21 | Panel Board Circuit Directories | FALSE
O22 | Valve Charts | TRUE
O23 | Attic Stock | FALSE
O24 | Attic stock delivered with tansmittals and acknowledgements of receipt | FALSE
O25 | Inventory spread sheet | FALSE
O26 | All stock labeled with Manufacturer name and model number | FALSE
SYSTEMS DEMONSTRATION AND TRAINING
# | Sub-Category | Applicable | Reference Link | Date of Completion | Date Approved | Person Responsible | Note
S1 | Training Manual | FALSE
S2 | Electronic copy - pdf format - for each system or equipment demonstrated and trained | FALSE
S3 | Contents | FALSE
S4 | Agendas | TRUE
S5 | Training Schedule | TRUE
S6 | Sign-In Sheets | FALSE
S7 | Training Handouts | FALSE
S8 | Include contact information for training videographer | TRUE
S9 | Training Recordings | FALSE
S10 | Digital video format | FALSE
S11 | Organized according to training schedule | FALSE
S12 | Digital video file naming should include project name and PR # | FALSE

## Preconstuction Mtg (GMP)
[5 empty] | GR Section | Paragraph
PROJECT KICK OFF - PRECONSTRUCTION MEETING (GMP Contracts) |  |  |  |  | 01 31 19 | 3.02
INITIAL PROGRESS MEETING
Within 7 days of contract issue / NTP
Led by Contractor - Minutes by Contractor
Attendees
USC PM, A/E, Safety, Quality,
GC PM & Precon Personnel
Agenda
Designation and introduction of key personnel and team members and their duties
Communication plan / lines of communication
Schedule Review
Long Lead Item Review
Phasing
Critical Work Sequencing
Minutes to be issued within 2 days of meeting. Draft comments within 2 days and formal issuance to follow
PRECONSTRUCTION COORDINATION MEETINGS
Held weekly or at frequency established by USC PM / A/E
Attendees
USC PM, A/E
GC PM & Precon Personnel
Major subcontractors & suppliers as required
Agenda
Items of significance that could affetc
Program
Scope
Design
Technical Issues
Budget
Schedule

## Sheet1
Meeting Information
| Project Name: |  |  | PR#: |  | Date: |  |  |  |  | Next Meeting Date:
| Meeting Name: | PreCon Mtg Stip Sum |  |  |  | Time: |  |  |  |  | Next Meeting Time:
Purpose:
Attendees
| Name |  | Role/ Title | Company |  | Phone Number |  | Name |  | Role/ Title | Company |  | Phone Number
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
Agenda and Minutes (Meeting #000 . Agenda Topic #000 . Subtopic #000)
(Agenda for Kick Off Meeting)
| 0.001 | Agenda Topic 1
| 0.002 | Agenda Topic 2
| 0.003 | Agenda Topic 3
(Meeting Minutes Template)
| 001.001.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.001.001 | Subtopic |  |  | Discussion
| 001.001.002 | Subtopic |  |  | Discussion
| 001.002.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.002.001 | Subtopic |  |  | Discussion
| 001.002.002 | Subtopic |  |  | Discussion
| 001.003.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.003.001 | Subtopic |  |  | Discussion
| 001.003.002 | Subtopic |  |  | Discussion

## Template
Meeting Information
Project Name: |  | Meeting Date: |  | Reference GR Section: | Minutes Prepared By: | Schedule Update Due:
Meeting Name: |  | Meeting Time: |  | Paragraph: | Minutes Due: | Monthly Report Due:
Purpose: |  | Next Meeting Date: |  | Timeline: | Frequency: | System for Submission:
PR#: |  | Next Meeting Time: |  | Meeting Lead: | Pencil Draft Pay App Due:
Attendees
Role | Name | Attended | Company | Phone Number
USC Project Manager |  | TRUE
Architect / Engineer (A/E) |  | TRUE
Safety Representative |  | TRUE
Quality Representative |  | TRUE
General Contractor Project Manager |  | TRUE
GC Preconstruction Personnel |  | TRUE
Agenda and Minutes (Meeting #000 . Agenda Topic #000 . Subtopic #000)
0.001 | Agenda Topic 1
0.002 | Agenda Topic 2
0.003 | Agenda Topic 3
0.004 | Agenda Topic 4
0.005 | Agenda Topic 5
0.006 | Agenda Topic 6
0.007 | Agenda Topic 7
0.008 | Agenda Topic 8
0.009 | Agenda Topic 9
Meeting Minutes:
001.001.000 | Topic |  |  |  | Discussion |  | Reference | Delegate | Due Date
001.001.001 | Subtopic |  |  |  | Discussion
001.001.002 | Subtopic |  |  |  | Discussion
001.002.000 | Topic |  |  |  | Discussion |  | Reference | Delegate | Due Date
001.002.001 | Subtopic |  |  |  | Discussion
001.002.002 | Subtopic |  |  |  | Discussion
001.003.000 | Topic |  |  |  | Discussion |  | Reference | Delegate | Due Date
001.003.001 | Subtopic |  |  |  | Discussion
001.003.002 | Subtopic |  |  |  | Discussion

## PreCon Mtg Stip Sum
Meeting Information
| Project Name: |  |  | PR#: |  | Date: |  |  |  |  | Next Meeting Date:
| Meeting Name: | PreCon Mtg Stip Sum |  |  |  | Time: |  |  |  |  | Next Meeting Time:
Purpose:
Attendees
| Name |  | Role/ Title | Company |  | Phone Number |  | Name |  | Role/ Title | Company |  | Phone Number
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
☑ | [6 empty] | ☑
Agenda and Minutes (Meeting #000 . Agenda Topic #000 . Subtopic #000)
(Agenda for Kick Off Meeting)
| 0.001 | Agenda Topic 1
| 0.002 | Agenda Topic 2
| 0.003 | Agenda Topic 3
(Meeting Minutes Template)
| 001.001.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.001.001 | Subtopic |  |  | Discussion
| 001.001.002 | Subtopic |  |  | Discussion
| 001.002.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.002.001 | Subtopic |  |  | Discussion
| 001.002.002 | Subtopic |  |  | Discussion
| 001.003.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.003.001 | Subtopic |  |  | Discussion
| 001.003.002 | Subtopic |  |  | Discussion

## INITIAL PROGRESS MEETING
Item | Details
Meeting Name | Initial Progress Meeting
Timeline | Within 7 days of contract issue / NTP
Meeting Lead | Contractor
Minutes Prepared By | Contractor
Minutes Due | Draft within 2 days, Final to follow
Attendees
Role | Name | Attended
USC Project Manager |  | TRUE
Architect / Engineer (A/E) |  | TRUE
Safety Representative |  | TRUE
Quality Representative |  | TRUE
General Contractor Project Manager |  | TRUE
GC Preconstruction Personnel |  | FALSE
Agenda Item | Agenda Topic
1 | Designation and introduction of key personnel and team members and their duties
2 | Communication plan and lines of communication
3 | Schedule review
4 | Long lead item review
5
6 | Critical work sequencing
Meeting Information
| Project Name: |  |  | PR#: |  | Date: |  |  |  |  | Next Meeting Date:
| Meeting Name: | Initial Progress Meeting |  |  |  | Time: |  |  |  |  | Next Meeting Time:
Purpose:
Attendees
| Name |  | Role/ Title | Company |  | Phone Number |  | Name |  | Role/ Title | Company |  | Phone Number
☑ |  |  | USC Project Manager |  |  |  | ☑
☑ |  |  | Architect / Engineer (A/E) |  |  |  | ☑
☑ |  |  | Safety Representative |  |  |  | ☑
☑ |  |  | Quality Representative |  |  |  | ☑
☑ |  |  | General Contractor Project Manager |  |  |  | ☑
☑ |  |  | GC Preconstruction Personnel |  |  |  | ☑
☑ | [6 empty] | ☑
Agenda and Minutes (Meeting #000 . Agenda Topic #000 . Subtopic #000)
(Agenda for Kick Off Meeting)
| 0.001 | Agenda Topic 1
| 0.002 | Agenda Topic 2
| 0.003 | Agenda Topic 3
(Meeting Minutes Template)
| 001.001.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.001.001 | Subtopic |  |  | Discussion
| 001.001.002 | Subtopic |  |  | Discussion
| 001.002.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.002.001 | Subtopic |  |  | Discussion
| 001.002.002 | Subtopic |  |  | Discussion
| 001.003.000 | Topic |  |  | Discussion |  |  |  | Reference |  |  | Delegate | Due Date
| 001.003.001 | Subtopic |  |  | Discussion
| 001.003.002 | Subtopic |  |  | Discussion

## Const Kick Off Mtg
|  |  |  | GR Section | Paragraph
| CONSTRUCTION KICK OFF MEETING |  |  | 01 31 19 | 3.05
No later than 7 days after contract award / NTP
Attendees
USC PM, A/E, Safety, Quality,
GC PM & Precon Personnel
Major subcontractors & suppliers as required
Agenda
Designation and introduction of key personnel and team members and their duties
Communication plan / lines of communication
Schedule Review
Long Lead Item Review
Phasing
Critical Work Sequencing
Contractor’s Quality Control Plan
Contractor’s Site Specific Health & Safety Plan Plan
Contractors list and schedule of required preinstallation meetings
Trimble - PMIS Design & Construction System of Record
Procedures for RFI's
Procedures for requesting changes to the scope of Work.
Procedures for testing and inspecting.
Procedures for processing Applications for Payment.
Distribution of the Contract Documents.
Submittal procedures.
LEED requirement
Preparation of record documents
Use of the premises and existing building including access, security and key check out
Owner’s occupancy requirements.
Work restrictions and working hours.
Responsibility for temporary facilities and controls.
Procedures for moisture and mold control.
Procedures for disruptions and shutdowns.
Construction waste management and recycling.
Parking availability.
Office, work, and storage areas.
Equipment deliveries and priorities.
First aid.
Security.
Progress cleaning.
SBE, DBE and Labor Compliance Programs, if any.
Minutes to be issued within 2 days of meeting. Draft comments within 2 days and formal issuance to follow
Construction Kick-Off Meeting – Overview
Item | Details
Meeting Name | Construction Kick-Off Meeting
Timeline | No later than 7 days after contract award / NTP
Purpose | Formal start of construction and alignment on procedures, safety, quality, and controls
Minutes Due | Draft within 2 days, Final to follow
Attendees & Attendance Check
Role | Name | Attended
USC Project Manager |  | FALSE
Architect / Engineer (A/E) |  | FALSE
Safety Representative |  | FALSE
Quality Representative |  | FALSE
General Contractor Project Manager |  | FALSE
GC Preconstruction Personnel |  | FALSE
Major Subcontractors (as required) |  | FALSE
Major Suppliers (as required) |  | FALSE
Agenda Items
# | Agenda Topic
1 | Designation and introduction of key personnel and team members and their duties
2 | Communication plan and lines of communication
3 | Schedule review
4 | Long lead item review
5 | Phasing
6 | Critical work sequencing
7 | Contractor’s Quality Control Plan
8 | Contractor’s Site-Specific Health & Safety Plan
9 | Contractors’ list and schedule of required preinstallation meetings
10 | Trimble – PMIS Design & Construction System of Record
11 | Procedures for RFIs
12 | Procedures for requesting changes to the scope of work
13 | Procedures for testing and inspecting
14 | Procedures for processing Applications for Payment
15 | Distribution of the Contract Documents
16 | Submittal procedures
17 | LEED requirements
18 | Preparation of record documents
19 | Use of the premises and existing building (access, security, key checkout)
20 | Owner’s occupancy requirements
21 | Work restrictions and working hours
22 | Responsibility for temporary facilities and controls
23 | Procedures for moisture and mold control
24 | Procedures for disruptions and shutdowns
25 | Construction waste management and recycling
26 | Parking availability
27 | Office, work, and storage areas
28 | Equipment deliveries and priorities
29 | First aid
30 | Security
31 | Progress cleaning
32 | SBE, DBE, and Labor Compliance Programs (if applicable)

## Preinstall Mtg
| PRE-INSTALLATION CONFERENCES |  |  | GR Section | Paragraph
|  | At project site and before each construction activity that requires coordination with other construction |  | 01 31 19 | 3.06
Led by Contractor - Minutes by Contractor
Attendees
USC PM, A/E, Safety, Quality, Specialty consultants, test and inspection consultants
GC PM, Superintendent & Personnel
Major subcontractors & suppliers as required
Manufacturers representatives
Fabricators
Agenda
Review construction progress & activities related to installation work
Contract Documents.
Options.
Related RFIs.
Related Change Orders.
Related construction work directives
Purchases.
Deliveries.
Submittals.
Review of mockups.
Possible conflicts.
Compatibility requirements.
Time schedules.
Weather limitations.
Manufacturer’s written instructions/recommendations.
Warranty requirements.
Compatibility of materials.
Acceptability of substrates.
Temporary facilities and controls.
Space and access limitations.
Regulations of authorities having jurisdiction.
Testing and inspecting requirements.
Installation procedures.
Coordination with other work.
Required performance results.
Protection of adjacent work.
Protection of construction and personnel.
LEED requirements
Conclusions
Do not proceed with installation if the conference cannot be successfully concluded
Initiate any corrective actions and provide supporting data to resolve impediments
Reconvene Pre-Installation conference
Secure written approvals to proceed
Pre-Installation Conference – Overview
Item | Details
Meeting Name | Pre-Installation Conference
Location & Timing | At project site; before each construction activity requiring coordination
Meeting Lead | Contractor
Minutes Prepared By | Contractor
Purpose | Coordinate installation work and resolve conflicts before execution
Attendees & Attendance Check
Role | Name | Attended (✔ / ✘)
USC Project Manager |  | FALSE
Architect / Engineer (A/E) |  | FALSE
Safety Representative |  | FALSE
Quality Representative |  | TRUE
Specialty Consultants |  | TRUE
Test & Inspection Consultants |  | FALSE
General Contractor Project Manager |  | FALSE
Superintendent |  | FALSE
GC Personnel |  | FALSE
Major Subcontractors (as required) |  | FALSE
Major Suppliers (as required) |  | FALSE
Manufacturer’s Representatives |  | FALSE
Fabricators |  | FALSE
Agenda Items – Installation Coordination
# | Agenda Topic
1 | Review construction progress and activities related to installation work
2 | Contract documents
3 | Options
4 | Related RFIs
5 | Related Change Orders
6 | Related construction work directives
7 | Purchases
8 | Deliveries
9 | Submittals
10 | Review of mockups
11 | Possible conflicts
12 | Compatibility requirements
13 | Time schedules
14 | Weather limitations
15 | Manufacturer’s written instructions and recommendations
16 | Warranty requirements
17 | Compatibility of materials
18 | Acceptability of substrates
19 | Temporary facilities and controls
20 | Space and access limitations
21 | Regulations of authorities having jurisdiction
22 | Testing and inspecting requirements
23 | Installation procedures
24 | Coordination with other work
25 | Required performance results
26 | Protection of adjacent work
27 | Protection of construction and personnel
28 | LEED requirements
Conclusions / Required Actions
# | Conclusion / Directive | Responsible Party | Status / Notes
1 | Do not proceed with installation if conference cannot be successfully concluded
2 | Initiate corrective actions and provide supporting data to resolve impediments
3 | Reconvene Pre-Installation Conference if required
4 | Secure written approvals to proceed

## Weekly OAC Mtg
| WEEKLY CONSTRUCTION COORDINATION MEETINGS (AKA "OAC MEETING") |  |  |  | GR Section | Paragraph
[5 empty] | 01 31 19 | 3.03-B
Led by Contractor - Minutes by Contractor
Attendees
USC PM, A/E, Safety, Quality, Specialty consultants, test and inspection consultants
GC PM, Superintendent & Personnel
Major subcontractors & suppliers as required
Agenda
Review, correct or approve minutes from previous week
Present "four week rolling" bar chart schedule
Revise construction schedule where revisions have been made / recognized
Construction safety.
Design status.
Contractor / Subcontractor present and future needs:
Interface requirements.
Sequence of operations.
Resolution of BIM component conflicts.
Submittal status - also review critical submittals needed in next 30 days
Deliveries.
Off-site fabrication.
Access.
Site utilization.
Temporary facilities and controls.
Work hours.
Hazards and risks.
Progress cleaning.
Quality and work standards.
Construction work directives
Change Orders.
Corrective action requests and non-conformance reports.
RFI status, with emphasis on RFI’s critical to upcoming work.
Status of pending claims and disputes.
LEED documentation status update,
Minutes to be issued within 2 days of meeting. Draft comments within 2 days and formal issuance to follow
Weekly Construction Coordination (OAC) Meeting – Overview
Item | Details
Meeting Name | Weekly Construction Coordination (OAC) Meeting
Frequency | Weekly
Meeting Lead | Contractor
Minutes Prepared By | Contractor
Purpose | Ongoing coordination of construction progress, safety, schedule, and issues
Minutes Due | Draft within 2 days, Final to follow
Attendees & Attendance Check
Role | Name | Attended (✔ / ✘)
USC Project Manager
Architect / Engineer (A/E)
Safety Representative
Quality Representative
Specialty Consultants
Test & Inspection Consultants
General Contractor Project Manager
Superintendent
GC Personnel
Major Subcontractors (as required)
Major Suppliers (as required)
Agenda Items
# | Agenda Topic
1 | Review, correct, or approve minutes from previous week
2 | Present “four-week rolling” bar chart schedule
3 | Revise construction schedule as required
4 | Construction safety
5 | Design status
6 | Contractor / Subcontractor present and future needs
6.1 | Interface requirements
6.2 | Sequence of operations
6.3 | Resolution of BIM component conflicts
6.4 | Submittal status (critical submittals for next 30 days)
6.5 | Deliveries
6.6 | Off-site fabrication
6.7 | Access
6.8 | Site utilization
6.9 | Temporary facilities and controls
6.1 | Work hours
6.11 | Hazards and risks
6.12 | Progress cleaning
6.13 | Quality and work standards
6.14 | Construction work directives
6.15 | Change Orders
6.16 | Corrective action requests & non-conformance reports
6.17 | RFI status (critical to upcoming work)
6.18 | Status of pending claims and disputes
6.19 | LEED documentation status update

## Monthly Report Mtg
[11 empty] | GR Section | Paragraph | GCs Section
| MONTHLY PROGRESS REPORT & MEETING | [9 empty] | 01 31 19 | 3.04 | 10.3.3
|  | Monthly progress and pencil draft review | [10 empty] | 10.3, 10.4, 10.5
Pencil draft pay app by 25th of month (GC 10.3.1)
Attendees
USC PM, A/E,
GC PM, Superintendent & Personnel
Major subcontractors & suppliers as required
Project Scheduler (Major Capital Projects)
Inspector of Record (Hospital / OSHPD Projects)
Agenda
Pencil draft pay app review
Field progress review and schedule
Construction schedule update 10 days prior to meeting
Narrative forecasting project status
Major activities with start finish dates
Completed items
Items with remaining durations
Logic changes
Added or delected activities by change order or CWD
Incoporate any final modifications to schedule
Submit updated schedule to USC PM via Trimble within 2 business days
Monthly Report
Submit minimum 4 days prior to meeting
Executive Summary
Items of concern
Project photos
Cost reports
COP and alternates status and reports
Document control logs
Master & Look ahead schedules
Financial status report
Overall status
Subcontractor status
DBE/SBE and Labor Compliance program status (if applicable).
Contractors construction schedule
Progress since last report
Identify on time ahead and behind schedule activities
Behind schedule recovery and commitments
Review schedule for next period
Summary schedule narrative per 01 32 13
Other Status Reports
Master List of Submittals status report.
Safety and security report.
QC Report, including status of correction of deficient items.
RFI status report.
Change Order Proposal Requests and COPs status report.
Status of pending agency reviews / approvals
Corrective action plans for agency approvals behind schedule
Status of record documentation.
Pending claims and disputes.
Updated copies of LEED materials tracking spreadsheet
Monthly Progress Meetings - within 7 days of end of each month
Monthly Progress Report & Meeting – Overview
tem | Details
Meeting Name | Monthly Progress Report & Meeting
Frequency | Monthly
Purpose | Review project progress, pay application, schedule, and overall project status
Pencil Draft Pay App Due | By 25th of each month (per GC 10.3.1)
Schedule Update Due | 10 days prior to meeting
Monthly Report Due | Minimum 4 days prior to meeting
Meeting Timing | Within 7 days of end of each month
System for Submission | Trimble (submit updated schedule within 2 business days after meeting)
Attendees & Attendance Check
Role | Name | Attended
USC Project Manager |  | FALSE
Architect / Engineer (A/E) |  | FALSE
General Contractor Project Manager |  | FALSE
Superintendent |  | FALSE
GC Personnel |  | FALSE
Major Subcontractors (as required) |  | FALSE
Major Suppliers (as required) |  | FALSE
Project Scheduler (Major Capital Projects) |  | FALSE
Inspector of Record (Hospital / OSHPD Projects) |  | FALSE
Agenda – Payment & Field Progress Review |  |  | Agenda – Monthly Report Submittal |  |  | Agenda – Financial Status Report |  | Agenda – Construction Schedule Review |  | Agenda – Other Status Reports
# | Agenda Topic |  | # | Report Section |  | # | Financial Report Item | # | Schedule Review Item | # | Status Report Item
1 | Pencil draft pay application review |  | 3 | Executive Summary |  | 4 | Overall financial status | 5 | Progress since last report | 6 | Master list of submittals status
2 | Field progress review and schedule |  | 3.1 | Items of concern |  | 4.1 | Subcontractor status | 5.1 | On-time, ahead, and behind schedule activities | 7 | Safety and security report
2.1 | Construction schedule update (10 days prior to meeting) |  | 3.2 | Project photos |  | 4.2 | DBE/SBE & Labor Compliance program status (if applicable) | 5.2 | Behind-schedule recovery and commitments | 8 | Quality Control (QC) report and deficient-item corrections
2.2 | Narrative forecasting project status |  | 3.3 | Cost reports |  |  |  | 5.3 | Review schedule for next period | 9 | RFI status report
2.3 | Major activities with start and finish dates |  | 3.4 | COP and alternates status and reports |  |  |  | 5.4 | Summary schedule narrative per 01 32 13 | 10 | Change Order Proposal Requests & COPs status
2.4 | Completed items |  | 3.5 | Document control logs | [5 empty] | 11 | Pending agency reviews / approvals
2.5 | Items with remaining durations |  | 3.6 | Master & look-ahead schedules | [5 empty] | 12 | Corrective action plans for delayed agency approvals
2.6 | Logic changes | [8 empty] | 13 | Status of record documentation
2.7 | Added or deleted activities by Change Order or CWD | [8 empty] | 14 | Pending claims and disputes
2.8 | Incorporate final modifications to schedule | [8 empty] | 15 | Updated LEED materials tracking spreadsheet
2.9 | Submit updated schedule to USC PM via Trimble within 2 business days

## Substantial Completion Mtg
| SUBSTANTIAL COMPLETION MEETING | [5 empty] | GR Section | Paragraph | GCs Section
[7 empty] | 01 77 00 | 1.05 | 10.6, 10.7, 10.8
Contractors List of Incomplete Items (Punch List)
USC + A/E add to Contractor Punch List as necessary
Provide dollar value for incomplete items and reasons why work is incomplete
Submittals prior to Substantial Completion
Minimum 10 days before prior to substantial completion inspection
Certificates of Release from Authorities having jusrisdiction
Unrestricted use of work
Access to serv ices and utilities
Occupancy permits / Certificate of Occupancy
Similar AHJ releases
Formally submit closeout submittals
Project Record Documents per 01 78 39
Operation & Maintenance Data per 01 78 23
Attic stock as specified in individual specification sections and as per 01 78 23
Final completion construction photographic documentation
Demonstration and Training documentation / videos per 01 79 00
Statement of Commissioning Completion from 3rd party CxA per 01 91 13
Damage or Settlement Surveys
Property surveys
Individual specification section specific warranties, workmanship bonds, maintenance service agreements, final certifications
Changeover information for occupancy, use, operation and maintenance
Procedures prior to Substantial Completion
Advise of insurance changeover requirements
Final changeover to permanent locks and keys. Advise on security changeover to USC personnel.
Complete system and equipment startup and testing including reports.
Provide statement of Commissioning Completion from 3rd party CxA
Perform preventative maintenance on equipment
Instruct Owner’s personnel in operation, adjustment, and maintenance of products, equipment, and systems
Advise Owner of changeover in heat and other utilities.
Terminate and remove temporary facilities from Project Site, along with mockups, construction tools, and similar elements.
Participate with Owner in conducting inspection and walkthrough with local emergency responders.
Touch up and otherwise repair and restore marred exposed finishes to eliminate visual defects.
Remove broken and scratched glass and replace with specified glass
Check fluid and gas carrying pipe systems, roofs, flashings, gutters and downspouts for leaks. Repair or replace as necessary.
Lubricate all moving parts of machinery and equipment as recommended by the manufacturers of the machinery and equipment.
Complete final cleaning requirements, including touchup painting.
Substantial Completion Inpsection
Submit written request for inspection minimum 10 days prior to date work will be completed
USC to review and elect to proceed with inspection or notify Contractor of unfulfilled requirements
USC prepares Certificate of Substantial Completion after inspection
USC may notify Contractor of items in need of completion prior to issuance of Certificate of Substantial Completion
Reinspection will be conducted to address items in need of completion prior to issuance of Certificate of Substantial Completion
Results of the completed reinspection will form the basis of requirements for final completion.
Project Warranties
Submit written warranties on request of Owner or Architect for designated portions of the Work where commencement of warranties other than date of Substantial Completion is indicated
Partial Occupancy
Submit warratites within 15 days of completion of designated portions of work
1 Year Period of Correction - Inspection Walk Through Date Scheduling
Establish a follow up walk through of the entire project at month 11 after the substantial completion date. Meeting invitation to all contractual parties.
Walk through will determine if any defiencies not previously observed have manifested and document and provide demand for corrections. Document this required meeting to all parties.
Substantial Completion Meeting – Overview
Item | Details
Meeting Name | Substantial Completion Meeting
Reference Section | GR Section 01 77 00
Paragraph | 1.05
Purpose | Verify readiness for Substantial Completion, coordinate inspections, warranties, and closeout deliverables
Contractor’s List of Incomplete Items (Punch List)
# | Requirement | Responsible Party | Notes / Status
1 | Contractor’s Punch List of incomplete items | Contractor
2 | Additions to Punch List as necessary | USC / A/E
3 | Provide dollar value for incomplete items and reasons for incompleteness | Contractor
Submittals Prior to Substantial Completion
(Submit minimum 10 days prior to Substantial Completion inspection)
A. Releases from Authorities Having Jurisdiction (AHJ)
# | Release Type | Submitted (✔ / ✘) | Notes
1 | Unrestricted use of work | FALSE
2 | Access to services and utilities | FALSE
3 | Occupancy Permit / Certificate of Occupancy | FALSE
4 | Similar AHJ releases | FALSE
B. Formal Closeout Submittals
# | Submittal Item | Reference Section | Submitted (✔ / ✘)
1 | Project Record Documents | 01 78 39 | FALSE
2 | Operation & Maintenance Data | 01 78 23 | FALSE
2.1 | Attic stock (as specified) | 01 78 23 | FALSE
3 | Final construction photographic documentation |  | FALSE
4 | Demonstration & Training documentation / videos | 01 79 00 | FALSE
5 | Statement of Commissioning Completion (3rd Party CxA) | 01 91 13 | FALSE
6 | Damage or Settlement Surveys |  | FALSE
7 | Property Surveys |  | FALSE
8 | Section-specific warranties, bonds, maintenance agreements, certifications |  | FALSE
9 | Changeover information for occupancy, operation & maintenance |  | FALSE
Procedures Prior to Substantial Completion
# | Procedure | Responsible Party | Completed (✔ / ✘)
1 | Advise of insurance changeover requirements | Contractor | FALSE
2 | Final changeover to permanent locks and keys | Contractor | FALSE
3 | Complete system and equipment startup & testing with reports | Contractor | FALSE
3.1 | Statement of Commissioning Completion from 3rd Party CxA | Contractor | FALSE
4 | Perform preventative maintenance on equipment | Contractor | FALSE
5 | Train Owner’s personnel in operation & maintenance | Contractor | FALSE
6 | Advise Owner of utility changeovers | Contractor | FALSE
7 | Remove temporary facilities, mockups & tools | Contractor | FALSE
8 | Participate in emergency responder walkthrough | Contractor / Owner | FALSE
9 | Repair marred exposed finishes | Contractor | FALSE
10 | Replace broken or scratched glass | Contractor | FALSE
11 | Check piping, roofs, flashings, gutters for leaks | Contractor | FALSE
12 | Lubricate all moving parts | Contractor | FALSE
13 | Complete final cleaning & touch-up painting | Contractor | FALSE
Substantial Completion Inspection Process
# | Step | Responsible Party | Status / Notes
1 | Submit written request for inspection (10 days prior) | Contractor
2 | Review and approval to proceed with inspection | USC
3 | Conduct Substantial Completion inspection | USC
4 | Issue Certificate of Substantial Completion | USC
5 | Notification of remaining completion items (if any) | USC
6 | Conduct reinspection for remaining items | USC
7 | Reinspection results become basis for Final Completion | USC
Project Warranties / Partial Occupancy
# | Requirement | Timing | Submitted (✔ / ✘)
1 | Written warranties for designated portions of Work | As requested | FALSE
2 | Warranties for Partial Occupancy areas | Within 15 days of completion | FALSE
1-Year Period of Correction
# | Requirement | Details | Status
1 | Schedule follow-up walk-through | Month 11 after Substantial Completion
2 | Issue meeting invitations | All contractual parties
3 | Identify latent deficiencies | Not previously observed
4 | Document & issue demand for corrections | Formal documentation to all parties

## Final Completion Mtg
|  | FINAL COMPLETION |  |  | GR Section | PP | GCs Section
|  |  | Certified list of incomplete items |  | 01 77 00 | 1.06 | 10.9
Endorsed by USC
List to state each item completed or otherwise resolved for acceptance
Certificate of Insurance - showing evidence of final - continuing coverage
Final pest control report and warranty
Submital all final permit and inspection rrecords as required in 01 78 39 Project Record Documents
Final Pay Application
Final statement of accounts
Sworn statement final payments to subcontractors and suppliers
Unconditional releases
All other requirements from General Requirements Division 01 sections, General & Supplementary Conditions
Inspection
Submit written request for final inspection
USC proceeds with inspection or notifies Contractor of incomplete items to be fulfilled.
USC will approve the final Certificate for Payment or will notify Contractor of construction that must be completed or corrected
1 Year Period of Correction - Inspection Walk Through Date Scheduling
Establish a follow up walk through of the entire project at month 11 after the substantial completion date. Meeting invitation to all contractual parties.
Walk through will determine if any defiencies not previously observed have manifested and document and provide demand for corrections. Document this required meeting to all parties.
Final Completion – Overview
Item | Details
Phase | Final Completion
Referenced Sections | GR Section 01 77 00 / 01 78 39
Purpose | Closeout of all contractual, administrative, and inspection requirements prior to final acceptance and payment
Final Completion Requirements
# | Requirement | GR Section | PP | GC’s Section
1 | Certified list of incomplete items | 01 77 00 | 1.06 | 10.9
1.1 | List endorsed by USC
1.2 | Each item to be stated as completed or otherwise resolved for acceptance
2 | Certificate of Insurance showing evidence of final continuing coverage
3 | Final pest control report and warranty
4 | Submittal of all final permit and inspection records per Project Record Documents | 01 78 39
5 | Final Pay Application
5.1 | Final statement of accounts
5.2 | Sworn statement of final payments to subcontractors and suppliers
5.3 | Unconditional releases
5.4 | All other requirements from Division 01 (General & Supplementary Conditions)
Final Inspection Process
# | Step | Responsible Party
1 | Submit written request for final inspection | Contractor
2 | Conduct inspection or notify Contractor of incomplete items | USC
3 | Approve Final Certificate for Payment or notify Contractor of required corrections | USC
1-Year Period of Correction – Walk-Through
# | Requirement | Details
1 | Walk-through scheduling | Establish follow-up walk-through at Month 11 after Substantial Completion
2 | Meeting invitation | Invitation to all contractual parties
3 | Deficiency review | Identify deficiencies not previously observed
4 | Documentation | Document deficiencies and issue formal demand for corrections to all parties